## Summary
1.0 Implementation and Deployment Services Overview
This Exhibit 3 (Implementation and Deployment Services Requirements) are the requirements that set forth the roles and responsibilities of the parties for the Application Implementation and Deployment Services to be provided. These are the services required to devise a well thought out and thorough approach, a standards and best practices based methodology and deployment plan, and a successful deployment of the CMS Application. The Implementation and Deployment Services shall include, but are not limited to the following: • Preliminary Business Analysis Services • Implementation Strategy and Approach Services • Deployment Planning Services • Court deployment including: o Implementation Project Management Services o Infrastructure Assessment Services o Operational Processes & Procedures Services o Application Configuration Services o Data Conversion Services o Data Integration Services o Document Management System Configuration Services o Testing Services o Cutover and Stabilization Services o Training Services • Implementation Project Management Services o Demonstrated ability in large deployment projects using PMI best practices o Proven methodologies for application project strategy development
Instructions: Tab 2 Implementation & Deployment Services - Please provide response to the questions. The Prospective Bidder may attach any additional pages required to fully address any of the requirements, provided each addition page is clearly labeled with the requirement number and category name/description to which it applies.
Instructions: Tab 3 Requirements, Tab 4 Service Levels, Tab 5 Definitions - The Court considers Prospective Bidder to agree to Exhibit 3, unless identified herein. Absence of issues will constitute agreement for those terms not herein addressed, and will be off the table for further negotiation.

## Implem. & Deploy Srvs
2.0 Implementation and Deployment Services
Item # | Implementation and Deployment Services | Response
2.1 | Describe your implementation planning process (including project management, best practices, Organizational Change Management, Communications, and Personnel management).
2.2 | Describe your recommendation for roles your company personnel will assume and the roles that Court staff should assume in the implementation process.
2.3 | Describe how your proposed management practices, procedures and tools conform to industry best practices and describe the benefits of your approach. Include coordination and control of deployment activities in order to identify and mitigate issues; overall approach to communicatioln at all levels for the life of the project; organizational change managment process; staffing level management process and personnel management process.
2.4 | Describe how you would manage the use of any required interfaces or electronic tools that have been purchased and/or installed. Examples of local interfaces may include jail management systems, booking systems, juvenile detention management systems, imaging systems, and probation systems.
2.5 | Describe the process involved in implementing any required specific configurations, e.g., local ordinances, terms of probation and pretrial release, and the creation of standard local documents using case management information. Identify any local Court personnel required to accomplish the task.
2.6 | Describe the process, resources, and expertise necessary in converting data from existing system into the new CMS.
2.7 | Describe your process for coordinating user acceptance.
2.8 | Describe your process for implementing change management.
2.9 | Describe your process for managing critical defect scenarios.
2.1 | Describe your process for coordinating software upgrades and version management.
2.11 | Describe the process employed to track and report progress in system deployment.
2.12 | Describe the process and standards employed in determining when phases of deployment are satisfactorily completed.
2.13 | Describe the process involved in implementing any required state and local configurations, e.g., implementation of state statutes and rules, creation of standard state documents, state calendar, etc. Include any Court personnel required to accomplish the task.
2.14 | Describe the process involved in assessing and recommending how the required hardware and software that will ensure improved performance for the end-users is to be achieved, and how it is scalable to meet the future needs of the Court

## Requirements
3.0 Implementation and Deployment Services
The following sections set forth the Vendor’s tasks, roles and responsibilities and the services for which the Vendor shall be responsible.
3.1 | Preliminary Business Analysis Services tasks, roles and responsibilities. Preliminary Business Analysis Services include the tasks, activities and deliverables required by the Vendor to gain sufficient knowledge about the Court environment and overall Court requirements to enable creation of an implementation strategy and approach, a deployment plan and to successfully deploy the Application. The following table identifies the Vendor’s and Court’s Preliminary Business Analysis Services tasks, roles and responsibilities. | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Participate in meetings with the Court to understand high-level court requirements, priorities and existing team and reporting structure within court. | X
| 2. Deliverable: Develop and present to court a Preliminary Business Analysis Plan that clearly highlights the Vendor recommended steps to obtain the required knowledge to start the deployment process. This plan should clearly articulate the key steps that will be performed by the Vendor for obtaining requisite knowledge as well as lay out the time and effort requirements from the court. | X
| 3. Review, approve and accept the Preliminary Business Analysis Plan. |  | X
| 4. Execute the Preliminary Business Analysis Plan and obtain the required knowledge to start the deployment process. | X
| 5. Deliverable: Document the results of Preliminary Business Analysis and present to Court. | X
| 6. Review, approve and accept the results of the Preliminary Business Analysis, |  | X
3.2 | Implementation Strategy and Approach Services Tasks, Roles and Responsibilities. Implementation Strategy and Approach Services are the activities and Deliverables associated with developing and refining the deployment and training strategy and approach and methodology that will be used for deployment of the proposed solution. The following table identifies the Vendor’s and Court’s Implementation Strategy and Approach Services tasks, roles and responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Document and present to Court the recommended Implementation Strategy and Approach, including a communication plan that accounts for all constituents (e.g., Courts and justice partners, etc.) and a technical environment plan that includes the scope and objectives of non-production and production environments. | X
| 2. Review, approve and accept the recommended implementation strategy and approach, communication plan, and technical environment plan. |  | X
| 3. Deliverable: Develop a Vendor Staffing Plan that identifies vendor staff levels required at various points in the project and supports the implementation strategy and approach. | X
| 4. Review, approve and accept the Vendor Staffing Plan. |  | X
| 5. Deliverable: Recommend a Court Staffing Plan identifies court staff levels required at various points in the project and that will support the implementation strategy and approach. | X
| 6. Deliverable: Develop and present to Court a detailed, standards-based methodology with proposed toolsets to complete this deployment initiative within time and budget. | X
| 7. Review, approve and accept the methodology and toolsets for deploying the application. |  | X
| 8. Deliverable: Provide recommendations on appropriate deployment of logical environments to support vendor’s recommended deployment strategy (e.g., testing, data conversion, etc.) | X
| 9. Review, approve and accept recommendations on appropriate deployment environments. |  | X
3.3 | Court Implementation Services
The Court Deployment Services are those services, as described in the following subsections that must be performed to successfully deploy the Application.
3.3.1.1 | Implementation Requirement: Implementation/Deployment Project Management Services
Deployment Project Management Services are the activities and Deliverables associated with developing and maintaining a Court Implementation/Deployment project Plan and schedule for deployment of the CMS application. The following table identifies the Vendor’s and Court’s Deployment Planning Services tasks, roles and responsibilities.
| Implementation/Deployment Project Management Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Develop, document and maintain the Implementation/Deployment Project Plan throughout the course of the engagement. This plan is based on the approved overall approach, methodology and use of proposed toolsets and processes. Vendor shall update this plan on a periodic basis as defined by Court (e.g., monthly, bi-monthly). This plan shall be developed and maintained in Microsoft Project software or an alternative project management tool approved by Court. This plan shall include all required details such as staffing, timelines, key activities, milestones, deliverables, actual progress against plan, variances, etc. Implementation/Deployment Project Plan will take into consideration Court holidays. | X
| 2. Review, approve and accept Implementation/Deployment Project Plan |  | X
| 3. Establish, maintain and update a Deployment Knowledge Base with all deliverables and documents within the scope of the Deployment Services. In addition to full and accurate documentation of the Vendor's own activities, Vendor will include in the Deployment Knowledge Base all documents, information and data on which they rely to perform Deployment Services, including but not limited to the following: configuration guides, training manuals, assessment reports, user manuals, system level setup and procedures, all queries, form templates, reports and tuning parameters around the database or servers. The Deployment Knowledge Base must be fully indexed and key word searchable. | X
3.3.2 | Deployment Requirements: Infrastructure Assessment and Implementation Services
Infrastructure Assessment and Implementation Services are the activities and Deliverables required to assess and to validate that all components of the Court’s technical infrastructure, which must be able to support the Application, DMS, and the traffic generated through their use. These components include, but are not limited to, desktops, laptops, network elements, scanners, printers, etc. Infrastructure Assessment and Implementation Services also include coordinating and managing the implementation of other needed components. The following table (Table 4) identifies the Vendor’s and Court’s Infrastructure Assessment and Implementation Services tasks, roles and responsibilities.
Vendor’s Infrastructure Assessments and Deployment Services will focus on evaluating Court’s infrastructure in four main areas:
1. Desktop Environment – Evaluation of desktop machines and devices, Operating System (OS), and required software components and printers.
2. Network Environment – Evaluation of bandwidth and capacity planning capabilities against anticipated traffic volumes due to implementation of the Application and DMS and projected growth.
3. Data Center Environment – Vendor will evaluate Court connectivity and environment readiness (e.g., Application, Data Exchange Infrastructure, DMS, etc.) based on the infrastructure recommendations from the Deployment Strategy and Approach and Planning phases.
4. Document Management System Environment – As part of DMS implementation, Vendor will undertake an assessment to determine additional infrastructure items (scanners, document scanning software, printers, and intermediate servers), storage requirements, and suitability for integration with Application integration components.
In addition, during the Infrastructure Assessment, Vendor will identify gaps, formulate recommendations, and communicate an action plan for Court to address the findings in the Infrastructure Assessment. Information will be shared with the Court at regular and pre-defined stages of the Assessment. Vendor will deliver the final Infrastructure Assessment Findings report to the Court for review and approval.
| Infrastructure Assessment and Implementation Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Develop and document an Infrastructure Assessment Plan and template for assessing all components of the Court’s technical infrastructure. | X
| 2. Review, approve and accept the Infrastructure Assessment Plan and template. |  | X
| 3. Perform the infrastructure assessment for all technical components for the Court. | X
| 4. Deliverable: Document and present to Court, the findings of the infrastructure assessment, including recommendations on specific areas that need to be upgraded, standardized or secured. | X
| 5. Review, approve and accept the findings of the infrastructure assessment. |  | X
| 6. Perform hardware and connectivity capacity planning for the Court. | X
| 7. Review, approve and accept hardware and connectivity capacity planning. |  | X
| 8. Deliverable: Document and present to Court an assessment of required hardware as well as the network infrastructure required at a minimum to support the rollout. | X
| 9. Review, approve and accept the hardware and network infrastructure assessment. |  | X
| 10. Manage the installation of any additional hardware or network infrastructure and coordinate with third parties as required. |  | X
| 11. Review, approve and accept the installed hardware or network infrastructure. | X
| 12. Measure bandwidth utilization per case type and minimum hardware required to support rollout. | X
| 13. Deliverable: Provide documented findings to the Court of the minimum requirements for desktop hardware along with bandwidth utilization numbers to support sizing of the network to the hosting data center. | X
| 14. Review, approve and accept documented findings. |  | X
3.3.3 | Deployment Requirement: Operational Process and Procedures Services
Operational Process and Procedures Services are the activities and Deliverables required to assess the existing Court case management processes and procedures, perform a gap analysis with the process options compatible with the Application and develop and document recommended case management operational processes and procedures the Courts will utilize with the Application.
| Operational Processes and Procedures Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Identify current operational processes and procedures used for case management by working in conjunction with the Courts. | X
| 2. Deliverable: Assess the existing (“as is”) operational processes and procedures against the end state (“to be”) Application configurations, processes and procedures, and develop recommendations on processes that will meet Court’s requirements. | X
| 3. Review, approve and accept the “as is” versus “to be” assessment and the process recommendations. |  | X
| 4. Deliverable: Document approved Court procedures in a Court-approved format. | X
| 5. Review, approve and accept approved Court procedures. |  | X
| 6. Deliverable: Develop and provide the Court with a business impact analysis based on the “as is” versus “to be” assessment. | X
| 7. Review, approve and accept the business impact analysis. |  | X
3.3.4 | Deployment Requirement: Application Configuration Services
Application Configuration Services are the activities and deliverables required to configure the Application to support the Court business processes. The following table identifies the Vendor’s and Court’s Application Configuration Services tasks, roles and responsibilities.
| Application Configuration Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Conduct training sessions/system walkthroughs for Court business process staff to provide an understanding of the application and business context for configurations. | X
| 2. Conduct SME Education Sessions about system and configuration impacts. | X
| 3. Identify end state (“to be”) configurations by working in conjunction with the Courts. | X
| 4. Deliverable: Develop a detailed application configuration strategy that will meet Court requirements. | X
| 5. Review, approve and accept the “as is” versus “to be” assessment and the configuration strategy. |  | X
| 6. Deliverable: Develop and document a detailed application configuration plan that links to data exchange configuration. | X
| 7. Review, approve and accept the detailed application configuration plan. |  | X
| 8. Deliverable: Create and maintain a detailed application configuration workbook incorporating all recommended Configuration Items (CIs). | X
| 9. Review, approve and accept the detailed application configuration workbook. |  | X
| 10. Configure approved CIs as documented in the detailed application configuration workbook into the Application. | X
| 11. Deliverable: Create and submit to Court a detailed configuration workbook listing the final application configuration details of the Application. | X
| 12. Review, approve and accept the configuration workbook. |  | X
| 13. Perform Application Configuration Services activities in synchronization with the Data Integration Services | X
| 14. Identify Forms, Notices, and Reports requirements and design by working in conjunction with the Court. | X
| 15. Deliverable: Forms, Notices, and Reports Design Documents |  | X
| 16. Review, approve and accept Forms, Notices, and Reports Design Documents. | X
| 17. Test approved configurations based on the Detailed Application Configuration Workbook. Unit test the configuration. | X
| 18. Identify defects and changes. |  | X
| 19. Remediate identified defects and changes. | X
3.3.5 | Deployment Requirement: Data Conversion Services
Data Conversion Services are the activities and Deliverables associated with the assessment, planning, mapping, scripting, conversion and testing required for the conversion of data from the current Court systems to the Application.
The following table identifies the Vendor’s and Court’s Data Conversion tasks, roles and responsibilities.
| Data Conversion Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Identify sources of data from the current Court systems by working in conjunction with the Court. | X
| 2. Deliverable: Assess the existing (“as is”) sources of data (including software, code, functionality, and data) against the end state (“to be”) Application, and develop a detailed Data Conversion Strategy and Data Conversion Plan for each source of data based on the assessment | X
| 3. Review, approve and accept the detailed Data Conversion Strategy and Data Conversion Plan. |  | X
| 4. Deliverable: For each source of data, develop and document the detailed data schema/maps from current systems to the Application. | X
| 5. Deliverable: For each source of data, identify and document data elements which cannot be converted through the automated tools and/or other exceptions and develop a plan to achieve data conversion through alternative means (e.g., manual conversion, manual entry). | X
| 6. Review, approve and accept mapping and plan for converting data elements which cannot be converted through automated tools and/or other exceptions. |  | X
| 7. Configure data conversion tools, as required to perform data conversion. | X
| 8. Provide all relevant technical documentation (development/configuration manuals etc.) on such data conversion scripts and tools. | X
| 9. Perform data conversion through automated or manual processes as approved by Court. | X
| 10. Deliverable: Create a comprehensive Data Conversion Test Plan for each source of data. | x
| 11. Review, approve and accept all Data Conversion Test Plans. |  | X
| 12. Deliverable: Conduct data conversion testing using Vendor’s validation process, identify errors and exceptions and document and provide a report on the testing results to Court. | X
| 13. Conduct data conversion re-testing until requirements are met. | X
| 14. Review, approve and accept conversion testing and retesting results. |  | X
3.3.6 | Deployment Requirement: Data Integration Services
Data Integration Services are the activities and Deliverables associated with the assessment, planning, design, development, modification, and testing of the data exchanges between the Court and county and state partners, and the Application. This includes justice partner exchanges, electronic filing and electronic services, as well as the Application portal. The following table identifies the Vendor’s and Court’s Data Integration Services tasks, roles and responsibilities.
| Data Integration Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Create an inventory of existing data exchanges (local and statewide exchanges) including internal, justice partner, vendor, and public facing exchanges and portal access, and create a Gap Analysis that assesses the existing (“as is”) state and scope of exchanges against the end state (“to be”) state and scope of exchanges. | X
| 2. Identify data exchange requirements between the current Court and partner systems and the Application, and analyze them against proposed data exchange standards, public access requirements, etc. and present recommended exchanges to the Court. | X
| 3. Ensure that such data exchange requirements between the current Court and partner systems and the Application are identified by working in conjunction with the Court and Court’s county and state justice partners (e.g., law enforcement, public defender, DOJ, DMV). Additionally, ensure that any gaps or exceptions identified in configuration or data conversion affecting data exchanges as well as deficiencies in the data exchange standards are also assessed. | X
| 4. Deliverable: Develop and provide to Court, a Gap Analysis that includes recommendations on the new exchanges that need to be configured and developed. | X
| 5. Review, approve and accept the Gap Analysis. |  | X
| 6. Discuss Gap Analysis results with Justice Partners. | X
| 7. Deliverable: Develop and maintain a detailed Data Exchange Deployment Plan consisting of the end-to-end process for exchange deployment (from the “as is” to the “to be” states) including organization of local data exchange deployment team, including Court, Vendor and justice partner resources, as needed. | X
| 8. Review, approve and accept the detailed Data Exchange Deployment Plan |  | X
| 9. Deliverable: Develop and maintain a data integration pre-testing activities workbook including connectivity of vendors/partners, development of Court policy file, and configuration of e-filing. | X
| 10. Review, approve, and accept the pre-testing activities workbook. |  | X
| 11. Perform the necessary activities to configure and deploy exchanges as required and approved by the Court. | X
| 12. Deliverable: Conduct data exchange deployment (for both local and statewide exchanges) and integration testing using Vendor’s validation process, identify errors and exceptions and document and provide testing and traceability matrix results to Court. | X
| 13. Conduct data exchange deployment and integration re-testing until requirements are met. | X
| 14. Review, approve and accept data exchange deployment and integration testing and retesting results. |  | X
| 15. Provide Court with one data integration technical subject matter expert, as requested by the Court. | X
| 16. Perform Data Integration Services activities in synchronization with the Application Configuration Services. | X
3.3.7 | Deployment Requirement: Document Management System (DMS) Configuration Services
Document Management System (DMS) Configuration Services are the activities and Deliverables associated with developing and implementing DMS infrastructure requirements and integrating the DMS with the Application at Court. The following table identifies the Vendor’s and Court’s Document Management System Configuration Services tasks, roles and responsibilities.
| Document Management System Configuration Services Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Develop a DMS Integration Plan and Approach for integrating existing Document Management Systems (DMS) with Application. | X
| 2. Review, approve and accept plan and approach for integrating existing DMS with Application. |  | X
| 3. Deliverable: For Courts that do not have an existing DMS, provide a plan and approach for: | X
· Gathering DMS requirements from the Court.
· Implementing the DMS infrastructure required at the Court level (e.g., scanners, intermediate servers).
· Integrating DMS use into Court-specific Application business processes (e.g., workflows).
· Integrating the Court’s DMS infrastructure with the hosted DMS application.
| 4. Review, approve and accept plan and approach for DMS infrastructure implementation and integration with Application for Courts that do not have an existing DMS. |  | X
| 5. Deliverable: Perform integration of (new as well as existing) DMS with Application. | X
| 6. Review, approve and accept integration of (new as well as existing) DMS with Application. |  | X
| 7. Coordinate the implementation of the DMS infrastructure required at the Court level and integrate with Application and the DMS application. | X
3.3.8 | Implementation Requirement: Testing Services
Testing Services are the activities and Deliverables associated with planning and executing testing for Acceptance by the Court of the entire set of contracted Deployment requirements (e.g., configuration, exchanges). The following table identifies the Vendor’s and Court’s Testing Services tasks, roles and responsibilities.
| Testing Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Develop, document and maintain a Test Plan for all Deployment Services, including the plan for end-to-end testing, network performance testing, data integration testing, application configuration testing, roles-based access testing and Court Acceptance testing. The Test Plan will define criteria for entering and exiting the various test phases. | X
| 2. Review, approve and accept the Test Plan. |  | X
| 3. Prepare and document test cases, test scripts and test data as required by the Test Plan. | X
| 4. Review, approve and accept test cases, test scripts, and test data. |  | X
| 5. Deliverable: Perform end-to-end testing, network performance testing, data integration testing, application configuration testing, mock cutover testing, and roles-based access testing, using industry standard methodologies and best practices. Such testing shall include testing for any and all Application release versions issued prior to a Court’s Final Acceptance of the Services. | X
| 6. Support Court Acceptance testing processes. | X
| 7. Conduct Court Acceptance testing. |  | X
| 8. Deliverable: Manage, identify, classify, and document to Court any Deployment Services-related deficiencies or errors found as a result of testing, using Court-prescribed tools. | X
| 9. Resolve Deployment requirements-related deficiencies and errors found as a result of testing. Such Resolution shall include retesting. | X
| 10. Deliverable: Document and provide to Court the testing and retesting and traceability matrix results for Court approval. | X
| 11. Develop any additionally needed test scripts for any subsequent Application releases prior to a Court’s Final Acceptance of the Services. | X
| 12. Review, approve and accept testing, retesting and traceability matrix results. |  | X
3.3.9 | Implementation Requirement: Cutover and Stabilization Services
Cutover and Stabilization Services are the activities and Deliverables required to successfully manage the Cutover from existing systems to the Application (“go live” support) without affecting the day-to-day functioning of the Court and ensuring that the transition process to the Application is completed quickly and in the most efficient manner possible. The following table identifies the Vendor’s and Court’s Cutover and Stabilization Services tasks, roles and responsibilities.
| Cutover and Stabilization Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Define and document to Court the Cutover and Stabilization Services Plan to be performed by Vendor. | X
| 2. Review, approve and accept the Operational Cutover and Stabilization Services Plan. |  | X
| 3. Perform and coordinate cutover activities in accordance with the Cutover and Stabilization Services Plan. | X
| 4. Provide expert on-site support to Court personnel during the Cutover, to ensure that the Cutover and transition are performed smoothly. | X
| 5. Provide expert on-site resolution of any issues or problems that may arise in the post-Cutover transition stabilization period and/or manage resolution through approved processes and procedures. | X
| 6. Perform all activities as provided, at minimum, in the court defined exit criteria. | X
| 7. Coordinate with Court help desk as required, including problem management and Incident management processes. | X
| 8. Train Court help desk and provide requisite help desk scripts and tools for Deployment Services and daily support and maintenance. | X
| 9. Review, approve and accept scripts. |  | X
3.3.10 | Implementation Requirement: Training Services
Training Services are the activities and Deliverables associated with training the Application configuration administrators and End-Users for the purpose of supporting the Application and fully utilizing the functions and features of the applications through formal training (which may include classroom training, computer or web based training) and informal methods during the Deployment. The following table identifies the Vendor’s and Court’s Training Services tasks, roles and responsibilities.
| Training Services Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Deliverable: Develop, document to Court and maintain a Court Training Plan, including training schedule, instructor requirements, court facilitator requirements, module/class structure, Court facilities requirements, alternative facility options, and specific training data issues. | X
| 2. Review, approve and accept the Court Training Plan. |  | X
| 3. Deliverable: Provide Application configuration and administration training to administrators. | X
| 4. Deliverable: Provide Application End-User training and Court help desk training. | X
| 5. Deliverable: Provide ongoing, pre-scheduled Application End-User training and Court help desk training for any subsequent Application releases prior to Court’s Final Acceptance of the Services. | X
| 6. Create and maintain the training configurations on the Application training instances as requested by Court. | X
| 7. Deliverable: Provide e-filing and DMS operational training to Court-specified End-Users. | X
| 8. Deliverable: Provide Court-specified End-Users with ongoing, pre-scheduled e-filing and DMS operational training for any subsequent Application releases prior to a Court’s Final Acceptance of the Services. | X
| 9. Review, approve and accept training. |  | X
| 10. Review, approve and accept justice partner training session. |  | X
3.4 | Implementation Requirement: Project Management Services
Implementation Project Management Services are the activities and Deliverables associated with providing project management throughout the term of the engagement. The following table identifies the Vendor’s and Court’s Implementation Project Management Services tasks, roles and responsibilities.
| Implementation Project Management Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Provide project strategy and direction including overall scope and timelines. |  | X
| 2. Provide, and review with Court, Vendor project metrics reporting on Vendor’s accomplishment of milestones, SLRs and associated Deliverables. | X
| 3. Review, approve and accept project metrics, SLRs, milestones and Deliverables. |  | X
| 4. Develop and present to the Court remediation plans to resolve Deployment Services related issues. | X
| 5. Review, approve and accept remediation plans to resolve Deployment Services related issues. |  | X
| 6. Deliverable: Participate in the creation of a Court-specific release plan. | X
| 7. Coordinate the Application releases between the Courts through the pre-production environments to the production environment. | X
| 8. Participate as requested by Court in technical and business planning/governance meetings to establish and communicate decisions. | X
| 9. Adhere to Court Incident and problem management processes and tools. | X
| 10. Vendor Project Manager shall schedule and conduct weekly project status meetings with appropriate Vendor resources in accordance with the Project Communications Plan with Court Project Manager and other key Court participants as the Court Project Manager may require. | X
| 11. Participate in weekly project status report meetings. |  | X
| 12. Deliverable: Provide written weekly project status reports to the Court Project Manager including status updates of applicable items in the Project Plan (e.g. the project schedule) in a format agreed to by Court, including escalation of any issues and risks that may impact Critical Milestones, as well as issue and risk mitigation actions. | X
| 13. Execute projects using PMI best practices including standard project life cycle activities, project initiation, planning, execution, control and closure, and Acceptance. | X
| 14. Coordinate all Services, activities and dependencies and serve as the single point of contact/interface to Court including coordinating Vendor, Third Party and Court resources to ensure the on-time delivery of tested/quality checked Deliverables as defined in the Project Plan. | X
| 15. Prepare and present a quarterly Executive Management Report in a mutually agreed upon format. | X
| 16. Deliverable: Provide a Change Management Plan outlining the review process for documenting and approving changes in project scope. | X
| 17. Provide single portal access for all documents and reports | X
| 18. Provide a regular Implementation Summary Report that includes current status of milestones, Court milestones, and all SLRs. | X
| 19. Review, approve and accept Implementation Summary Report. |  | X
| 20. Deliverable: Develop overall approach and strategy to manage and maintain a Deployment Knowledge Base that will contain deployment documents and Deliverables from Court deployment, including recommendations on content, structure and tools. | X
| 21. Review, approve and accept overall approach and strategy to manage and maintain a Deployment Knowledge Base. |  | X
| 22. Deliverable: Manage and maintain the Court-specified Deployment Knowledge Base throughout the Application deployment process, incorporating Application documents and Deliverables. | X
| 23. Deliverable: Update the Deployment Knowledge Base with all deliverables and documents for Court as a part of Cutover and Stabilization Services. | X
| 24. Review, approve and accept the updated Deployment Knowledge Base after all deliverables and documents. |  | X
3.5 | Implementation Requirement: Customer Satisfaction Management Services
Customer Satisfaction Management Services are the activities associated with developing, implementing and reporting on Customer Satisfaction surveys to the Court Project Management team. The following table identifies Vendor’s and Court’s Customer Satisfaction Management Services tasks, roles and responsibilities.
| Customer Satisfaction Management Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Establish Customer Satisfaction Survey requirements for Court. |  | X
| 2. Deliverable: Develop Customer Satisfaction Survey in accordance with Court’s survey requirements. | X
| 3. Review, approve and accept Vendor developed Customer Satisfaction Survey. |  | X
| 4. Conduct quarterly Customer Satisfaction Surveys to the Court. |  | X
| 5. Meet with Court to review Customer Satisfaction reports and make recommendations on how to resolve customer dissatisfaction. | X
| 6. Deliverable: Prepare a Customer Satisfaction Project Plan to resolve customer dissatisfaction. | X
| 7. Review, provide additional input as required, approve and accept Customer Satisfaction Project Plan. |  | X
| 8. Execute Court-Accepted Customer Satisfaction Project Plan. | X
3.6 | Additional Services Available to Courts
3.6.1 | Document Scanning Services |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
Data Conversion Services are: (1) the activities and Deliverables associated with the assessment, planning, mapping, scripting, performing data conversion and testing for the conversion of data from the current Court systems to the Application; and (2) the activities and Deliverables associated with scanning documents into the DMS, linking these documents to their appropriate actions in the Application and performing quality assurance testing to ensure that documents have been properly scanned and linked.
3.6.1.1 | Manual Data Entry and Scanning Services |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
Where desired by a Court, Vendor will provide the following document scanning and manual data services.
Vendor will work with the Court to define and document local scanning and manual data entry requirements including the quantity and type of documents to be scanned. Load scripts will be developed for linking the scanned images back into the Application. It is the Court’s responsibility to provide the documents in accordance with the requirements herein regarding Data Safeguards.
3.6.1.2 | Document Manual Conversion Strategy |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
Vendor will develop the details surrounding what information needs to be manually converted. The following is a list of tasks associated with the Manual Conversion Strategy Deliverable:
1. Determine legacy elements that will not be programmatically converted using the developed conversion routines. The Court will have an opportunity to decide whether there is value in manually converting the data—in other words, does the data warrant manual conversion (e.g., document scanning) or can the data remain in the hard copy case file?
2. Determine the elements in the Application that will be assigned a default value as a result of missing legacy data. Some legacy systems will not have the information needed to create an entity in the Application. Therefore, Vendor will work with the Court to identify what default values or assumptions are needed to allow for legacy case processing in the Application.
3. Determine the fields that are affected by the missing or defaulted data and provide a plan for correcting or completing the information in the Application. This task gives the Court visibility on what business processes (if any) may need to be reviewed in order to support the data structure because this may include a workaround or a manual data entry during Court case processing.
3.6.1.3 | Manual Data Entry |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
Manual conversion is addressed through the execution of manual data entry.
For manual data entry efforts, Vendor will provide the Court with a template data mapping guide and will work with the Court to complete the guide to support manual data entry activities. The Court is responsible for acquiring and entering the data required by the guide. The data mapping guide will:
Lay out the types of documents that are to be manually data-entered and the process that a non-Court staff member would use to quickly recognize and categorize the legacy documents.
Identify the data elements that should be extracted from each of the legacy document types to be manually data-entered.
Identify the mapping of legacy record type to the Application record type.
Explain the types of data anomalies that are likely to be encountered in each legacy record type and the process that should be used to resolve or flag each of these issues.
In order to support manual data entry efforts, the Court will provide one day of training per legacy system on the specifics of manually entering case file data from that Court.
Additionally, the Court will provide Monday-through-Friday telephone contact, during Court business hours, with an individual who can respond to questions from data entry Vendor Staff and provide direction on how to proceed with specific data entry issues.
Manual data entry will be done on a case management entity-by-entity basis. Case management entities include base case data, participant record, event record, disposition record, dismissal, judgment, and filing information. Note that creating a case through manual data entry will involve entering many component case management entities.
For the purposes of manual data entry, a record is defined as a case management entity such as a case initiation, filing, participant, judgment, or event. The Court will determine the minimum information that must be entered for each entity.
3.6.2 | 3.6.2 Conduct Document Scanning at the Court |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
Vendor resources will conduct document scanning for a Court. The Court will provide facilities for the imaging team. Vendor will bring document preparation and imaging equipment and resources to use at the Court. The Court will be responsible for provision of space, tables, power, and general office equipment to support any on-site scanning to be undertaken. All space shall be located in such a way to minimize the need for Vendor Staff to move documents long distances or between floors and buildings between the document preparation and quality control process. The space available limits the number of imaging workstations and personnel that can work concurrently and will impact the overall schedule. A minimum of 200 square feet is required to support a single threaded imaging workflow.
On-site scanning work will be structured in such a way that an imaging team can come to the Court and work 40 hours per week continuously until work is complete.
Courts will commence local scanning for documents received subsequent to the files being removed for bulk scanning. The Vendor Staff will develop an approach for appending the documents scanned at the Court and at the Vendor location into a single file at time of Cutover.
Steps included in this task include:
1. Document Preparation. Files will be reviewed and prepared for scanning. Files will be extracted from the storage containers or file folders, and placed in trays for production. Tray header sheets containing a barcode identifying the originating box will be generated from the scanning system and placed in each tray for inventory control and tracking purposes. Each tray header barcode will then be scanned into the scanning system, beginning the tracking of individual trays containing folders. The trays will then be transferred to the production area.
Vendor will prepare the Case Files for scanning by removing blank pages from the files, removing any fasteners such as paper clips and staples, unfold, orient the pages up-right read-right, and tape any tears to limit further damage from conversion equipment. Files to be converted were likely compiled by a variety of sources and therefore are likely in a mixed condition and state of preparedness. Files may contain various page sizes, paper weights, background colors, ink colors, and document conditions. Patch cards will be placed between each folder and will be read by the scanner to indicate the beginning of a new folder for document sequencing purposes.
2. Imaging. Documents will be imaged and then reviewed through a quality control process to catch scanning and pagination errors.
Vendor will scan pages to TIFF, group IV image files or other format as required by the AOC (e.g., .PDF) and determine that pages within the file are scanned. Scanning will be done in duplex mode to capture images from double-sided forms.
A Scanning Operator will scan the tray header into the scanning system. The Operator will remove the files from the tray and begin the scan process. As the documents are being scanned the capture system will detect that it has encountered a file header sheet and will automatically create a new batch. The Scanning Operator will visually compare images being scanned to look for skewed pages; double fed documents, missed batch level or document level barcodes, and any documents that may have been scanned improperly (additional reviews occur during quality assurance and indexing functions). If the Scanning Operator should find any problems, the functionality must be present to rescan, insert, or delete any pages at the scan station.
During the scanning process, each page will be assigned a unique Document Control Number (DCN). The DCN provides the ability to track a certain page back to the file level, tray level, and box level.
3. Indexing. Once scanned, documents are sent to an indexing group where they are reviewed and the appropriate data elements are added to the document metadata so that they can be attached to the case management record in the Application. Indexing is limited to a single data element such as a document ID number.
The images will be routed to Indexing to create digitization of the required fields. A final edit program applies any applicable business rules defined by Court to perform checks on the data for validation. Errors found are routed to an experienced indexer to make the necessary corrections.
3.6.3 Document Scanning and Manual Data Entry Services Roles and Responsibilities
The following table identifies the Vendor’s and Court’s Manual Data entry and Document Scanning Services tasks, roles and responsibilities.
| Document Scanning and Manual Data Entry Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Determine Overall Document Scanning Approach. | X
| 2. Identify Types of Documents to be scanned. |  | X
| 3. Identify Meta-Data to be attached to the scanned documents. | X
| 4. Identify the Mapping of the scanned document to the Application Record. | X
| 5. Identify Potential Data Anomalies. |  | X
| 6. Provide training to data entry Vendor staff. |  | X
| 7. Review documents to be scanned for Exceptions. |  | X
| 8. Modify documents as needed to reduce Exceptions. |  | X
| 9. Prepare documents for scanning or manual entry. | X
| 10. Develop data mapping guide. | X
| 11. Deliverable: Manual Data Conversion Report. | X
| 12. Review, approve and accept Manual Data Conversion Report. |  | X
| 13. Deliverable: Scanning Completion Report. | X
| 14. Review, approve and accept Scanning Completion Report. |  | X
| 15. As required, perform redaction of scanned/converted data. |  | X
| 16. Index Documents scanned. | X
| 17. Provide telephone support for scanning, data entry and indexing Vendor Staff. |  | X
| 18. Attach scanned Documents to Case Management Records in the CCMS Application. | X
| 19. Return Documents. | X
| 20. Submit Results of scanning activities. | X
3.7 | E-filing Implementation Services |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
If the Court elects to implement E-filing functionality in this deployment, then the Vendor shall support the Court in the implementation of e-filing as described below:
Develop e-filing documentation. The Court Deployment Team’s integration resources will develop documentation to support the Court in the selection of an Electronic Filing Service Provider (EFSP) and the implementation of e-filing at the Court.
Procurement Documentation. The Court Deployment Team will compile a set of specifications and services that the EFSP must provide to the Court for the Court to bundle with their normal procurement documentation and conduct a selection. The team will also compile a set of evaluation criteria that the Court can use to help select the most appropriate EFSP vendors.
Policy File. Initially, in time for the procurement, and then again, as e-filing is implemented and readied for testing, the Vendor will produce the e-filing Court policy file.
3.7.1 | Provide implementation support. |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
As the EFSP prepares to implement, Vendor will support and coordinate implementation services.
Assist in evaluation of EFSP submissions. Vendor will review the submissions provided by the EFSPs who respond to the Court’s RFP, and will make recommendations as to which EFSP submissions are technically compliant with the requirements of the Application and the data exchange infrastructure.
Coordinate integration with the Court. As the EFSP prepares to connect to the system, Vendor will work with the selected EFSP and the Court to arrange for access and network connectivity.
Coordinate Data Exchange Configuration. In the event that the e-filing module requires configuration to support a specific EFSP, Vendor will advise the Court. The Court is responsible for resolving data exchange infrastructure issues.
3.7.2 | Provide testing support.
| Vendor will coordinate and lead the Courts and EFSP through the integration and end-to-end testing. |  |  | Issue | Proposed Solution/Rationale and Benefit to the Court
Develop and Maintain a Data Exchange Deployment Testing Plan. E-filing will follow a very similar process to other interfaces in that a test plan will be used to track (1) the requirements that will be verified during testing, and (2) the test scenarios that will be used.
Coordinate data integration and application configuration services. When planning to test e-filing, the Court Deployment Team’s integration resources will coordinate activities with the other deployment threads. Vendor will update the environment with the appropriate configuration and release version, help confirm the network security and performance, and provide the current data set. Testing will be conducted within a test environment (established by the Court) that simulates production.
Coordinate and lead integration testing. Vendor will coordinate and lead integration testing. The Court is responsible for resolving issues associated with data exchanges and associated infrastructure. Issues with the EFSP’s interface will be reported to the EFSP for remediation.
Coordinate and lead end-to-end testing. Vendor will coordinate and lead end-to-end testing of all CMS and integrated components. The Court is responsible for resolving issues associated with the data exchange infrastructure. Issues with the EFSP’s interface will be reported to the EFSP for remediation.
Compile test results. Vendor will compile test results of the e-filing implementation to document the level of functionality obtained.
Conduct data exchange deployment and integration re-testing. Vendor will continue end-to-end testing for up to eight weeks. The Court is responsible for resolving issues associated with data exchange infrastructure. The EFSP and/or the Justice Partner is responsible for resolving issues with its interface. If the exchange has not successfully passed end-to-end testing within the defined eight week timeframe, Vendor will suspend testing and the exchange will be considered to have failed the deployment readiness gate.
| E-filing Implementation Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Develop e-filing policy file. | X
| 2. Review e-filing policy file. |  | X
| 3. Develop e-filing Specifications. | X
| 4. Evaluate and recommend EFSP Submissions. | X
| 5. Select EFSP. |  | X
| 6. Coordinate EFSP connection with data center. |  | X
| 7. Deliverable: Data Exchange Deployment Testing Plan | X
| 8. Review, approve, and accept the pre-testing activities workbook. |  | X
| 9. Build/Tailor Test Plan to meet local Court needs. | X
| 10. Lead E-filing Integration Testing. | X
| 11. Lead E-filing End to End Testing. | X
| 12. Deliverable: Test Results | X
| 13. Conduct data exchange deployment and integration re-testing. | X
| 14. Review, approve and Accept data exchange deployment and integration testing and retesting results. |  | X
| 15. Maintain the data exchange infrastructure with respect to capacity and connectivity to support the Application development, test, and production deployment environments. |  | X
| 16. Provide support for integration work from integration resources. | X
| 17. Pre-Cutover readiness testing. | X
| 18. Provide Cutover support. | X
| 19. Manage post Cutover issue triage for local exchanges. | X
| 20. Resolve issues with partner system. |  | X
| 21. Resolve Issues with data exchange infrastructure. |  | X
| 22. Conduct Remediation of data exchange infrastructure configuration. |  | X
| 23. Conduct Remediation Coding of data exchange infrastructure |  | X

## Service Levels
4.0 Service Level Requirements
A key objective of this outsourcing agreement is to attain Service Level Requirements (SLRs). SLRs associated with Deployment Services are detailed in the following section.
Vendor shall provide electronic reports to the Court regarding Vendor’s compliance with the SLRs specified in the Master Services Agreement.
Table 1. Variance to Deployment Plan SLRs
Definition | Measurement of the variance between the Vendor and Court agreed completion dates of key project activities, milestones and Deliverables identified in the Deployment Plan and actual completion dates.
Type | Service Measure | Performance Target | SLR Performance
Adherence to Deployment Plan Key Activities and Milestones | Variance from Deployment Plan | Variance of key activities and milestones dates < 10% | 100%
| Formula | (Number of milestone dates missed)/Total number of milestone dates
| Measurement Interval | Measure Monthly
| Reporting Period | Report Monthly
| Measurement Tool | TBD
Table 2. Customer Satisfaction SLRs
Definition | Court shall conduct Customer Satisfaction surveys to measure the Customer Satisfaction SLRs as provided below.
Customer Satisfaction SLR
Customer Satisfaction | Service Measure | Performance Target | SLR Performance
Court deployment team | Court Satisfaction rate | Court’s designated deployment team and management team members (as defined by the Court) surveyed should be very satisfied or satisfied | 90%
| Formula | Number of participants responding to a Scheduled Survey that they are very satisfied or satisfied (as defined by the AOC)/Total number of participants responding to such Scheduled Survey
| Measurement Interval | Measure Quarterly
| Reporting Period | Report Quarterly
| Measurement Method/Source Data | TBD
Table 3. Post Deployment Incident Resolution SLRs
Definition | Time to Resolve Incidents and Problems to different Priority Level classifications following Incident classification as a configuration/implementation Incident. This pertains to Incidents and problems occurring between the “Go-Live” date and the end of the Cutover period for the Court.
Incident Resolution SLRs
Incident Resolution | Service Measure | Performance | SLR Performance %
Target
Severity 1 or 2 Incident Notification | Time to respond | < 15 minutes | All 100% ONLY
Severity Level 1 | Time to Resolve | < 4 hours | 100%
Severity Level 2 | Time to Resolve | < 8 hours | 100%
Severity Level 3 | Time to Resolve | < 40 hours | 100%
Severity Level 4 | Time to Resolve | 15 days | 90%
Root Cause Analysis | Time to report | Within 24 hours of Incident Resolution for Priority Level 1 or 2 | 100%
| Formula | Number of requests completed within performance target/total of all requests occurring during Measurement Interval
| Measurement Interval | Measure Weekly
| Reporting Period | Report Monthly
| Measurement Tool | TBD
Table 4. Priority Levels
Priority Level | Description
1 - Emergency/Urgent | A Priority Level 1 Incident is generated if it is an incident based on configuration, data conversion, data exchange or FNR (Forms, Notices and Reports) activities and has severely impacted the application or component such that the application or component cannot reasonably continue to operate and there is no Workaround available.
2 - High | A Priority Level 2 Incident is generated if it is an incident based on configuration, data conversion, data exchange or FNR (Forms, Notices and Reports) activities and has severely impacted the application or component such that the application or component cannot reasonably continue to operate, but a Workaround is available.
3 - Medium | A Priority Level 3 Incident is generated if it is an incident based on configuration, data conversion, data exchange or FNR (Forms, Notices and Reports) activities and has impacted the application or component such that the non-critical component of the application is unavailable, will not work or is not operating as expected and there is a Workaround available.
4 - Low | A Priority Level 4 Incident is generated if there is a Problem other than Priority Level 1, Priority Level 2, and Priority Level 3 Incidents.

## Definitions
5 | Requirements Definitions
5.1 | “Application” means the complete case management system, including all associated software, data exchanges, and external systems to be implemented by Vendor.
5.2 | “Court Training Plan” means the plan that the Vendor shall develop for Court respecting End-User and configuration administrator Application training.
5.3 | “Critical Milestones” means those milestones, activities, actions and projects identified as such in this Agreement, but are not limited to this Agreement. Additional milestones may be negotiated by individual courts.
5.4 | “Customer Satisfaction” means a subjective rating obtained through Court customer satisfaction surveys conducted from time to time in accordance with terms defined herein.
5.5 | “Cutover” means going-live on (i) the Application, or (ii) one or more case types within the Application, in each case (x) at one or more Court locations, and (y) where all Court personnel who are provided access to case management system(s) by the Court are able to access the Application and perform their normal daily operations using the production environment of the Application.
5.6 | “E-filing Court Policy File” means the technical specification and policy schema for submitting documents electronically to the court.
5.7 | “Fee Reductions” means the dollar amount by which the Fees will be reduced based on Vendor's failure to timely achieve any Critical Milestone. Fee Reductions may be defined and specified herein or by an individual trial court.
5.8 | “Final Acceptance” means Court written Acceptance of all Services and Deliverables including Court signoff on all exit criteria as defined in the Cutover and Stabilizations Services.
5.9 | “Incident” means either a (i) single event or (ii) abnormal activity for a function monitored by Vendor, each requiring a Vendor response typically denoted by a request for service or identification of a problem. Court will determine the Incident Priority Level of each reported Incident. Vendor will provide Court with an escalation procedure (to be approved by Court) for resolution of reported and non-reported incidents.
5.1 | “Incident Resolution” means the point at which Vendor has responded to an Incident and Vendor has either: (a) conducted and successfully completed a Root Cause Analysis on a problem and appropriately corrected both the results and the cause of the problem; or (b) has provided an appropriate answer to an inquiry or an informational question that is understood by and acceptable to Court. In both cases, the Incident is not resolved until Court is convinced and satisfied that it has been resolved.
5.11 | “Court Implementation and Deployment Project Plan” means the plan that Vendor shall develop for Court with respect to the Implementation/Deployment Services, as defined in Exhibit 3.
5.12 | “Knowledge Transfer Plan” means the plan the Vendor shall develop and execute respecting the knowledge required for Vendor to start the implementation process, as defined in Exhibit 3.
5.13 | “Measurement Interval” means the period in which a given SLR is measured (e.g., one (1) month, one (1) year, etc.).
5.14 | “Measurement Tool” means a tool used to measure processes, equipment, and networks systems.
5.15 | “Performance Target” is defined as the desired level of service Court is seeking for that particular Service Level Requirement.
5.16 | “Priority Level” is a defined category that identifies the degree of business criticality and importance to Court of specific Incidents and the associated Vendor response requirements attributed to any such Incident. The Priority Level table categories and descriptions set forth in Exhibit 3 apply to all Services.
5.17 | “Reporting Period” means the interval of time between providing reports. Unless otherwise specified, all reports are provided on a monthly basis within three (3) Business Days of the close of the calendar month.
5.18 | “Resolve” or “Resolution” means to repair, replace, reconfigure, reinstall, re-route, or otherwise provide a complete solution to an Incident that returns the system and/or End-User(s) to non-degraded full functionality. Implementing a Workaround is a partial or temporary resolution.
5.19 | “Root Cause Analysis” is a problem analysis process undertaken to identify and quantify the underlying cause(s) of an Incident and document the necessary corrective actions to be taken to prevent recurring problems and/or trends which could result in problems.
5.2 | “Implementation Plan” means the plan for deployment of the Application that the Vendor shall develop and maintain throughout the course of the Implementation/Deployment Services in accordance with Exhibit 3.
5.21 | “Workaround” is a temporary solution that Vendor or Court can implement in the event of an Incident as an alternate method of providing full Service or process functionality that allows the affected system(s) and/or process(es) to deliver to Court an acceptable level of business operations functionality until a permanent Incident Resolution can be implemented. Any such Workaround must be acceptable to and approved by Court.